## Sheet4
Requirement | Function | Finish
1 | Registration of organization (I want to be able to register multiple organizations) | 100%
2 | Register / invite members (users) to the organization | 100%
3 | Create channel (group chat) | 100%
4 | Send and receive messages to the group chat | 100%
5 | Want to distinguish between a public channel | 100%
6 | Adding star to the message, and then display a list of starred messages. | 0%
7 | Want to be in thread form in reply to the message | 0%
8 | Want to make mentionable by @user name | 0%
9 | Want to check the number of unread messages | 0%
Step
Step1. | Let’s build Rails development environment | 100%
Step 1-1: Ruby install
Step 1-2: Rail install
Step 1-3: Database (MySQL) install
Step2. | Let’s create a repository on GitHub | 100%
Step3. | Create a Rails Project | 100%
Step4. | Imagine the application you want to create | 100%
Step5. | Set database connection settings ( peripheral settings ) | 100%
Step6. | Let's create an organizational model | 100%
Step 6-1: Let's be able to view, register, update and delete organizations
Step7. | Create users, channel models and CRUDs in a way that is tied to an organization | 100%
Step 7-1: Let's be able to list / create / detail / edit channels
Step 7-2 : Let me post messages to the channel/Group
Step 7-3 : Let's be able to delete the message
Step 7-4 : Let's look back at the added code
Step8. | Let's touch SQL | 100%
Step9. | Write an E2E test (User Interface testing) | 0%
Step10. | Let's share the Japanese part of the app | 100%
Step11. | Let's set the Rails time zone | 100%
Step12. | Let's set the validation | 80% | user sign_up,user login,workspace(create,edit),group(create,edit)
Step13. | Let's deploy | 100%
Step14. | Let's add channel/Group details | 80%
Step15. | Let me search for messages | 100%
Step16. | Let's add pagination | 40%
Step17. | Let's apply the design | 60%
Step18. | Let's make it available to multiple people (user introduction) | 0%
Step19. | Let's implement login / logout function | 100%
Step20. | Let's implement the user management screen | 50%
Step21. | Let's add a role to a user | 20%
Step22. | Let's set the error page properly | 100%

## Sheet1
Step1